## CDGD Jobs and Housing
APPENDIX A
GROWTH DEAL |  | SSLEP Confidential report GD Programme Delivery and Outputs Forecasting JOBS | [10 empty] | Outputs RAG - current position against forecast JOBS
Scheme title | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | JOBS Delivered to date | % of 2019-20 target attained to date | JOBS Forecast by March 2020 | JOBS Forecast by March 2021 | JOBS Forecast 2021-22+ | ORIGINAL forecast (by 2025)
Lichfield Park | [12 empty] | 0 | 0% | 200 | 400 | 723 | 1100
Meaford | [12 empty] | 80 | 100% | 80 | 500 | 2200 | 2200
Bericote Four Ashes (Phases 1 and 2) | [12 empty] | 495 | 47% | 1060 | 1160 | 1360 | 1080
SWAR | [12 empty] | 0 | 0% | 50 | 50 | 100 | 0
Branston Locks | [12 empty] | 0 | N/A | 0 | 460 | 3800 | 3844
Tamworth Enterprise Quarter | [12 empty] | 72 | 150% | 48 | 98 | 98 | 98
Spode Church Street Phase 2 | [12 empty] | 0 | 0% | 20 | 20 | 20 | 20
Keele SIH | [12 empty] | 0 | N/A | 0 | 38 | 80 | 80
Etruria Valley | [12 empty] | 0 | 0% | 500 | 1000 | 2200 | 2200
Churnet Works WITHDRAWN | [12 empty] | 0 | 0% | 0 | 0 | 0 | 0
Redhill (S) | [12 empty] | 17 | 19% | 89 | 220 | 220 | 125
Keele IC5 (S) | [12 empty] | 162 | 137% | 120 | 120 | 120
i54 (S) | [12 empty] | 80 | 62% | 130 | 190 | 190
Stoke on Trent Railway Station Power Upgrade | [12 empty] | 0 | N/A | 0 | 12 | 12 | 12
Victoria Ground Phase 2 | [12 empty] | 0 | N/A | 0 | 40 | 40 | 40
Blythe Park Extension Infrastructure project | [12 empty] | 0 | N/A | 0 | 190 | 415 | 415
SME Expansion programme | [12 empty] | 0 | N/A | 0 | 314 | 314
Apprenticeships - AME South Staffs College | [12 empty] | 107 | 100% | 107 | 107 | 107 | 107
Apprenticeships - AME NSCG | [12 empty] | 47 | 100% | 47 | 47 | 47 | 47
Apprenticeships - AME JCB | [12 empty] | 146 | 100% | 146 | 146 | 146 | 146
Skills Equipment Fund 1 | [12 empty] | 0 | N/A | 626 | 626 | 626 | 626
Skills Equipment Fund 2 | [12 empty] | 0 | N/A | 0 | 285 | 285 | 285
|  | Growth Deal - Jobs totals | [10 empty] | 1206 | 39% | 3223 | 6023 | 13103 | 11214
GROWTH DEAL |  | SSLEP GD Programme Delivery and Outputs Forecasting - HOUSING | [10 empty] | Outputs RAG - current position against forecast HOUSING
Scheme title | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | HOUSES Delivered to date | % of 2019-20 target attained to date | HOUSES Forecast by March 2020 | HOUSES Forecast by March 2021 | HOUSES Forecast 2021-22+ | ORIGINAL forecast (by 2025)
SWAR | [12 empty] | 163 | 74% | 220 | 320 | 2350 | 2200
Branston Locks | [12 empty] | 28 | 31% | 90 | 340 | 2500 | 2500
Stoke on Trent Railway Station Power Upgrade | [12 empty] | 0 | N/A | 0 | 21 | 21 | 21
Victoria Ground Phase 2 | [12 empty] | 0 | N/A | 0 | 63 | 63 | 63
Blythe Park Extension Infrastructure project | [12 empty] | 0 | N/A | 0 | 0 | 168 | 168
Stafford Gateway Land Acquisition | [12 empty] | 0 | N/A | 0 | 0 | 48 | 48
SME Expansion ptogramme | [12 empty] | 0 | N/A | 0 | 130 | 130
|  | Growth Deal - Housing totals | [10 empty] | 191 | 56% | 310 | 874 | 5280 | 5000
CITY DEAL | SSLEP City Deal Programme Delivery and Outputs Forecasting - JOBS
Keele SEND (City Deal) | [12 empty] | 0 |  | TBC | TBC | 440
DHN (City Deal) | [12 empty] | 0 |  | TBC | TBC | 229
AME Hub Phase 1 | [12 empty] | 12 | 100% |  |  | 12
Innovative Growth in Stoke-on-Trent and Staffordshire (IGISS) | [12 empty] | 251 | 113% |  |  | 222
Stoke-on-Trent and Staffordshire Business Support Programme (SSBSP) | [12 empty] | 196 | 147% |  |  | 134
Stoke-on-Trent and Staffordshire Business Support Programme (SSBSP) Business Loan Fund | [12 empty] | 251 | 104% |  |  | 241
|  | City Deal - Jobs totals | [10 empty] | 710 | 55% |  |  | 1278
Outputs
Outputs - benefits realisation
15. Children's contract signature
Construction
Outputs - benefits realisation
Construction/
LEP intervention
Construction/
LEP intervention
Construction/Delivery
Construction/Delivery - LEP intervention
Construction/
LEP intervention
Construction/
LEP intervention
Construction/Delivery - LEP intervention
Construction/Delivery - LEP intervention
Construction/Delivery - LEP intervention
Contruction/
LEP intervention
Construction/
LEP intervention
Construction
Construction
Construction
Construction/
LEP intervention
Construction/
LEP intervention
Outputs
Phase 1
Outputs
Phase 2
Outputs - benefits realisation
TODAY
Outputs - benefits realisation
Outputs - benefits realisation
Outputs - benefits realisation
Outputs - benefits realisation
Outputs
Outputs
Outputs
Outputs
Outputs
Out
puts
Outputs
Outputs - benefits realisation
Construction/
LEP intervention
land purchase
Construction/Delivery - LEP intervention
Contruction/
LEP intervention
Construction
Construction
Construction
Outputs
Phase 2
Outputs - benefits realisation
Outputs - benefits realisation
Out
puts
Outputs
Outputs
Outputs - benefits realisation
Construction/Delivery - LEP intervention
Construction/Delivery - LEP intervention
Construction/Delivery - LEP intervention
Construction/Delivery - LEP intervention
WITHDRAWN AUG 2019
Outputs
Outputs - benefits realisation
Outputs - benefits realisation
Outputs - benefits realisation
Outputs - benefits realisation
Outputs - benefits realisation
Outputs - benefits realisation
Outputs - benefits realisation