CEO Report

Period: Nov/Dec 2021

This report sets our progress made by the operational team to support Board strategy and ambitions locally. It specifically details progress made against the agreed Delivery Plan to ensure transparency, accountability and promote good governance. It also provides insight into the staffing resources and related risks. The delivery Plan has been operationalised and directly informs operation team priorities and individual work programmes.

Delivery Plan Action update:

1. **Governance**: continue to drive strategic change through evidenced-based, ambitious strategy underpinned by robust governance; a platform for future growth

|  |  |
| --- | --- |
| **Qtr3: Oct-Dec** | **Progress** |
| AGM + formal appointment of new NEDsInduction of new NEDs | CompletedN/A at this time |
| Strategy review/refreshStructural reviewReview of Governance and of associated Assurance Framework Implementation of any recommendations emerging from:* review of accountabilities
* Mid-Year Review
 | SSLEP Board subgroups have reviewed their current position in light of strategic changes/emerging new policy. A strategy refresh will commence in Jan 2022 when the future role of the LEP is made clear.Not yet commenced: A Structural review, Review of Governance and the implementation of the review of accountabilities (delivered by Hatch) will take place once the purpose and function of the LEP is made clear. The Hatch Review will help to inform any future changes |

1. **Operations**: continue to progress local projects and initiatives, demonstrating high-impact delivery of capital schemes and test-bed projects, whilst developing granular-level insight to support policy and investment decisions.

|  |  |
| --- | --- |
| **Qtr3: Oct-Dec** | **Progress** |
| Programme Management/M&E of grant programmes incl LGF / GBF / GPF / EZ’s / ESIF / City Deal  | Sharon continues to proactively project manage the significant LGF and GBF programmes and liaises regularly with individual programme managers leading on GPF, EZ, ESIF, City Deal etc, to ensure that regular reporting into Exec Board occurs.Our aim is to work with the collective programme management ‘team’ to ensure consistency of reporting across the investment portfolio |
| Recruitment of Growth Hub leadSITREP modelling/testing Incl. new economic briefing notes developed for local leaders Business Support Review Commission | JD share with T&F Group and Executive Board therefore prepared to action as soon as the LEP Review is concluded.SITREP design team (GC Business) and telemarketing function (Team Telemarketing) appointed. Stakeholder co-design meeting held 15/11/21. Test-bed surveys commenced 08/12/21 with full roll out planned for Jan 22To action once Head of Growth Hub in post, as a key opportunity for them to engage and learn about the local landscape delivery partners |

1. **Stakeholder engagement**: building mutually-beneficial relationships at a local/regional/national level whilst amplifying the voice of business and the brand of our place.

|  |  |
| --- | --- |
| **Qtr3: Oct-Dec** | **Progress** |
| Monthly 121 with all LA Leaders/CEOSCovid response task forceNetwork of Networks eventStrategic engagement with local initiatives and working groups to accelerate growthChampioning the interests of SOT/Staffs through strategic engagement with Midlands Engine/LEP Network/Peers/ Government | 121s taking place on a regular basis improving communication and collaboration between ourselves and local partners. This month’s engagements include: Economic growth district directors, Staffordshire Moorlands DC, Lichfield DC and Tamworth BCThe Taskforce has been a useful forum for local leaders to share information and agree action. The group has paused given the re-opening of the economy but an appetite exists for future meetings of this nature. Next meeting planned 21 Dec 21No further meetings in 2021Activity this month included engagement with:Lichfield DC Peer Review, Growth Hub, SOT Opportunities Taskforce, South Staffordshire (EDNA input), Keele University Future Staffordshire event, Staffordshire Chamber AGM, Countywide Redundancy Task Force, Jobs 22 launch, Meetings held this month include: Midlands Energy Hub Board, Department for International Trade, Midlands Energy Summit, Inst Economic Dev, Midlands Connect, Midlands LEP peers, Made Smarter  |
| Business engagement: test-bed survey launchThought leadership: series of round table events - economic changes/recovery/net zero etc Strategy refresh consultation | Test-bed commences 8 Dec and rolled out Jan/Feb 22Not yet commenced: All planning/preparation in place, to commence Jan 22.To commence post-strategy refresh |

Staffing:

* No Change

Operational risks:

**Demand on resources**: Local and regional partners continue to engage with the LEP team and seek input into local plans and developments. Limited resources hamper our ability to engage as widely as we could, impeding our ability to influence and add-value.

**Loss of key personnel**: Whilst current staff contracts provide agility in terms of scaling up/winding down the organisation, it also exposes fragility in the temporary nature of contracts. Of the 3.3 FTE resource, 1.5 FTE could be lost within 1 month (notice period), impacting on organisational memory and capacity. LEPs across the country are experiencing staffing disruption due to uncertainty created by the extended LEP Review.